## GanttChart
Dashboard, SSMC | [8 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com.
Student:Tao-Yung Yu,Zhongbo Ge,Hongtao Wang
| Project Start Date | 2019-09-11 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
[9 empty] | 2019-09-09 | [6 empty] | 2019-09-16 | [6 empty] | 2019-09-23 | [6 empty] | 2019-09-30 | [6 empty] | 2019-10-07 | [6 empty] | 2019-10-14 | [6 empty] | 2019-10-21 | [6 empty] | 2019-10-28
 | time axis 2019-09-09 to 2019-11-03
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2019-09-09 to 2019-11-03
1 | Review the current system ui
1.1 | Try to understand how the current system ui to be drawn |  |  | 2019-09-11 | 2019-09-17 | 7 | 80% | 5
1.2 | Learn the Ajax and jQuery knowledge |  |  | 2019-09-18 | 2019-09-24 | 7 | 0% | 5
2 | Understand basic logic
2.1 | develop SQL query to generate raw data |  |  | 2019-09-11 | 2019-09-11 | 1 | 0% | 1
2.2 | understand how to calculate WPH |  |  | 2019-09-12 | 2019-09-17 | 6 | 50% | 4
2.3 | develop SQL Query for 28 logics |  |  | 2019-09-18 | 2019-09-26 | 9 | 0% | 7
2.4 | check query result |  |  | 2019-09-27 | 2019-10-01 | 5 | 0% | 3
2.5 | check and record query efficiency |  |  | 2019-10-02 | 2019-10-08 | 7 | 0% | 5
3 | Design
3.1 | (A) Flexible Report
3.1.2 | Complete front-end prototype design. |  |  | 2019-09-25 | 2019-09-29 | 5 | 0% | 3
3.1.3 | Review front-end prototype design by supervisor. |  |  | 2019-09-30 | 2019-10-01 | 2 | 0% | 2
3.2 | (B) Simple report(11)
3.2.2 | Complete front-end prototype design. |  |  | 2019-10-02 | 2019-10-05 | 4 | 0% | 3
3.2.3 | Review front-end prototype design by supervisor. |  |  | 2019-10-06 | 2019-10-07 | 2 | 0% | 1
3.3 | (c) Report(3)
3.3.2 | Complete front-end prototype design. |  |  | 2019-10-08 | 2019-10-09 | 2 | 0% | 2
3.3.3 | Review front-end prototype design by supervisor. |  |  | 2019-10-10 | 2019-10-10 | 1 | 0% | 1
3.4 | (D) report contain diagram(2)
3.4.2 | Complete front-end prototype design. |  |  | 2019-10-11 | 2019-10-14 | 4 | 0% | 2
3.4.3 | Review front-end prototype design by supervisor. |  |  | 2019-10-15 | 2019-10-15 | 1 | 0% | 1
3.5 | (E) report contain diagram(3)
3.5.2 | Complete front-end prototype design. |  |  | 2019-10-16 | 2019-10-16 | 1 | 0% | 1
3.5.3 | Review front-end prototype design by supervisor. |  |  | 2019-10-17 | 2019-10-17 | 1 | 0% | 1
5 | Set up environment
5.1 | set up environment for connection between database and ASP.NET |  |  | 2019-10-09 | 2019-10-09 | 1 | 0% | 1
6 | Coding
6.1 | (A) Flexible Report
6.1.1 | Complete front-end Coding. |  |  | 2019-10-18 | 2019-10-24 | 7 | 0% | 5
6.1.2 | Complete front-end unit test. |  |  | 2019-10-25 | 2019-10-26 | 2 | 0% | 1
6.1.3 | Complete back-end Coding. |  |  | 2019-10-10 | 2019-10-16 | 7 | 0% | 5
6.1.4 | Review back-end Coding by supervisor. |  |  | 2019-10-17 | 2019-10-18 | 2 | 0% | 2
6.1.5 | Complete back-end unit test. |  |  | 2019-10-19 | 2019-10-21 | 3 | 0% | 1
6.1.6 | Complete the integration of the front and back end. |  |  | 2019-10-27 | 2019-10-29 | 3 | 0% | 2
6.1.7 | Complete integration test. |  |  | 2019-10-30 | 2019-10-30 | 1 | 0% | 1
6.1.8 | Complete the integration with Engineering Dashboard System. |  |  | 2019-10-31 | 2019-11-06 | 7 | 0% | 5
6.1.9 | UAT |  |  | 2019-11-07 | 2019-11-11 | 5 | 0% | 3
6.2 | (B) Simple report(11)
6.2.1 | Complete front-end Coding. |  |  | 2019-11-12 | 2019-11-14 | 3 | 0% | 3
6.2.2 | Complete front-end unit test. |  |  | 2019-11-15 | 2019-11-17 | 3 | 0% | 1
6.2.3 | Complete back-end Coding. |  |  | 2019-11-12 | 2019-11-14 | 3 | 0% | 3
6.2.4 | Review back-end Coding by supervisor. |  |  | 2019-11-15 | 2019-11-17 | 3 | 0% | 1
6.2.5 | Complete back-end unit test. |  |  | 2019-11-18 | 2019-11-18 | 1 | 0% | 1
6.2.6 | Complete the integration of the front and back end. |  |  | 2019-11-19 | 2019-11-19 | 1 | 0% | 1
6.2.7 | Complete integration test. |  |  | 2019-11-20 | 2019-11-20 | 1 | 0% | 1
6.2.8 | Complete the integration with Engineering Dashboard System. |  |  | 2019-11-21 | 2019-11-24 | 4 | 0% | 2
6.2.9 | UAT |  |  | 2019-11-25 | 2019-11-27 | 3 | 0% | 3
6.3 | (c) Report(3)
6.3.1 | Complete front-end Coding. |  |  | 2019-11-28 | 2019-11-29 | 2 | 0% | 2
6.3.2 | Complete front-end unit test. |  |  | 2019-11-30 | 2019-12-02 | 3 | 0% | 1
6.3.3 | Complete back-end Coding. |  |  | 2019-11-28 | 2019-11-29 | 2 | 0% | 2
6.3.4 | Review back-end Coding by supervisor. |  |  | 2019-11-30 | 2019-12-02 | 3 | 0% | 1
6.3.5 | Complete back-end unit test. |  |  | 2019-12-03 | 2019-12-03 | 1 | 0% | 1
6.3.6 | Complete the integration of the front and back end. |  |  | 2019-12-04 | 2019-12-04 | 1 | 0% | 1
6.3.7 | Complete integration test. |  |  | 2019-12-05 | 2019-12-05 | 1 | 0% | 1
6.3.8 | Complete the integration with Engineering Dashboard System. |  |  | 2019-12-06 | 2019-12-06 | 1 | 0% | 1
6.3.9 | UAT |  |  | 2019-12-07 | 2019-12-09 | 3 | 0% | 1
6.4 | (D) report contain diagram(5)
6.4.1 | Complete front-end Coding. |  |  | 2019-12-10 | 2019-12-10 | 1 | 0% | 1
6.4.2 | Complete front-end unit test. |  |  | 2019-12-10 | 2019-12-10 | 1 | 0% | 1
6.4.3 | Complete back-end Coding. |  |  | 2019-12-10 | 2019-12-10 | 1 | 0% | 1
6.4.4 | Review back-end Coding by supervisor. |  |  | 2019-12-11 | 2019-12-11 | 1 | 0% | 1
6.4.5 | Complete back-end unit test. |  |  | 2019-12-11 | 2019-12-11 | 1 | 0% | 1
6.4.6 | Complete the integration of the front and back end. |  |  | 2019-12-12 | 2019-12-12 | 1 | 0% | 1
6.4.7 | Complete integration test. |  |  | 2019-12-12 | 2019-12-12 | 1 | 0% | 1
6.4.8 | Complete the integration with Engineering Dashboard System. |  |  | 2019-12-13 | 2019-12-13 | 1 | 0% | 1
6.4.9 | UAT |  |  | 2019-12-13 | 2019-12-13 | 1 | 0% | 1
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## Sheet1
Milestone | Deadlines
(A) Flexible Report
Complete front-end prototype design. | 2019-10-03
Complete front-end Coding. | 2019-10-24
Complete front-end unit test. | 2019-10-26
Complete back-end Coding. | 2019-10-16
Review back-end Coding by supervisor. | 2019-10-18
Complete back-end unit test. | 2019-10-21
Complete the integration of the front and back end. | 2019-10-29
Complete integration test. | 2019-10-30
Complete the integration with Engineering Dashboard System. | 2019-11-06
UAT | 2019-11-11
(B) Simple report(11)
Complete front-end prototype design. | 2019-10-09
Complete front-end Coding. | 2019-11-14
Complete front-end unit test. | 2019-11-17
Complete back-end Coding. | 2019-11-14
Review back-end Coding by supervisor. | 2019-11-17
Complete back-end unit test. | 2019-11-18
Complete the integration of the front and back end. | 2019-11-19
Complete integration test. | 2019-11-20
Complete the integration with Engineering Dashboard System. | 2019-11-24
UAT | 2019-11-27
(c) Report(3)
Complete front-end prototype design. | 2019-10-14
Complete front-end Coding. | 2019-11-29
Complete front-end unit test. | 2019-12-02
Complete back-end Coding. | 2019-11-29
Review back-end Coding by supervisor. | 2019-12-02
Complete back-end unit test. | 2019-12-03
Complete the integration of the front and back end. | 2019-12-04
Complete integration test. | 2019-12-05
Complete the integration with Engineering Dashboard System. | 2019-12-06
UAT | 2019-12-09
(D) report contain diagram(5)
Complete front-end prototype design. | 2019-10-17
Complete front-end Coding. | 2019-12-10
Complete front-end unit test. | 2019-12-10
Complete back-end Coding. | 2019-12-10
Review back-end Coding by supervisor. | 2019-12-11
Complete back-end unit test. | 2019-12-11
Complete the integration of the front and back end. | 2019-12-12
Complete integration test. | 2019-12-12
Complete the integration with Engineering Dashboard System. | 2019-12-13
UAT | 2019-12-13